## Sheet1 (hidden)
Employee | Role My Application
Eka Kolagawati | Employee Jakarta
Bambang Shindiko | Employee Jakarta
M. Syukri | Employee Jakarta
Susie Handayani | Employee Jakarta | v
Agit F. Fajeri | Employee Jakarta/Auditor Assistant | v
Kelik Rahmatullah | Employee Jakarta/Admin Car | v
Ardika Putra | Employee Surabaya | v
Miranda Tara | Employee Surabaya | v
Afriani Nurdin | Employee Surabaya/Audit Assistant
Cendy Susanty | Employee Surabaya/Inflo | v

## UAT-1 (hidden)
Catatan UAT 21.12.2020
No | Description |  | Status | Remarks
1 | Susie Handayani | Personal details kosong | Closed | perlu di test ulang
| Agit F. Fajeri | Personal details kosong
| Kelik Rahmatullah | Personal details kosong
| Ardika Putra | Personal details kosong
| Miranda Tara | Personal details kosong
| Cendy Susanty | Personal details kosong
2 | Cendy Susanty | menu meeting room rsv yang surabaya tidak tampil | Open
| Ardika Putra | map: Emp Surabaya
Miranda Tara
Afriani Nurdin
Cendy Susanty
3 | Car Rsv perlu ditambahkan info driver 1 lagi. Detail menunggu dikirimkan oleh RSM |  | Closed
4 | Bu Eka login a.n Pak Amir. Informasi certification: released date= invalid date. Coba di cek lagi datanya |  | Open
5 | Meeting Room schedule bar tidak tampil, tapi event sudah ter create. (done) |  | Closed
6 | tambahkan file matrix service di career development. Tambah card baru. File di onedrive (done) |  | Closed
7 | Certification: Minova handle released date = release/start from. Perlu disesuaikan lagi data API nya di post oleh minova |  | Open
8 | informasi Employee Detail terkait perlu disesuaikan: |  | Open
| Office: | - Jakarta
- Surabaya
| Group: | - ECS
- ICS
- Senior Advisory
- BOP
9 | untuk tanggal yang masih 9999 agar bisa dijadikan "-" saja apabila tidak ada data |  | Open
10 | My Confirmation belum bisa submit |  | Closed

## UAT- 2 (hidden)
| Catatan UAT 22.12.2020 | Open
In Progress
Closed
No | Item | Status | Remarks
1 | Penambahan Tipe Partner of the Year di master data reward | Open | Parameterize
2 | Approve by -> dirubah menjadi Sign by di master data reward dan indiciplinary | Open | Parameterize
3 | Kantor -> dirubah menjadi Office di master data Facility | Open | Parameterize
4 | Di Master Data Certification, field certification Description diganti menjadi issued by | Open | Parameterize
5 | Nama lisensi yang ada agar bisa dipersingkat, butuh konfirmasi dari pihak RSM | Open | Menunggu data
6 | Published by ->dirubah menjadi Issued by pada master data lisensi | Open | Parameterize
7 | Fixed Term Contract -> dirubah menjadi Fixed Term | Open | Parameterize
8 | Quota cuti ingin agar bisa di generate auto setiap tanggal hiring masing2 employee | Open | to be confirm untuk solusinya
9 | Pada report masterdata employee history agar bisa dibuatkan search by job | Open | Penambahan filter

## UAT- 3 (hidden)
| Catatan UAT 23.12.2020 | Open
In Progress
Closed
No | Item | Status | Remarks
Web Portal
1 | Tanggal di give approval masih tampil double | In Progress
2 | link to inbox/outbox pada nama di timeline tidak bisa tampil | In Progress
3 | nama saat posisi on going di give approval tidak nyala biru | In Progress
4 | request kalau sudah selesai belum hilang, masih tampil terus | In Progress
5 | Di Menu Knowledge Management -> Policies & Procedures: ada tambahan IT, Data Security & Privacy. Document ada di Onedrive | Closed
6 | My Leave Record, yang on progress masih tampil. Harusnya yang tampil hanya yang sudah approve | In Progress
7 | Leave Record jumlah cuti masih berdasarkan calendar, harusnya itu ambil informasi sesuai yg ada di minova | Open
8 | masih ada file yang access nya masih bisa download | In Progress
9 | Bu Eka dan Pak Syukri tidak bisa access aplikasi Minova dari laptop. Tapi bu eka dari PC bisa akses | Open
10 | ditambahkan notifikasi asterix di Request and Approval berupa angka di request & approval | Open
11 | ditambahkan notifikasi asterix di employee spotlight sebagai penanda ada item baru. Dan kalau sudah di cek nanti tanda item barunya hilang. | Open
12 | Pak Syukri tidak bisa login ke yammer | Closed
13 | Werbpart opening agar bisa di set MLT karena narasi ada yang berupa Pointer. | Open
14 | Group Senior Advisory & BOP | Open
Mobile
15 | di Mobile employee ID belum yang AP, masih pake 00000xxx |  | noted akan di deliver, timeline to be confirm
16 | label Grade agar di ganti menjadi Level |  | to be confirm untuk solusinya, terkait dengan apk seluruh Client Minova
17 | Firm diganti semuanya dengan RSM Indonesia |  | to be confirm untuk solusinya, terkait dengan apk seluruh Client Minova
18 | Area diganti menjadi Employee Area |  | to be confirm untuk solusinya, terkait dengan apk seluruh Client Minova
19 | Point diganti menjadi Employee Office |  | to be confirm untuk solusinya, terkait dengan apk seluruh Client Minova
20 | History pengajuan cuti di mobile terkait pengajuan yang dari web belum tampil (Archive) |  | noted akan di deliver, timeline to be confirm
21 | setelah file di attach untuk pengajuan cuti, filenya tidak bisa dilihat oleh user yang mengajukan dan juga oleh approvernya |  | noted akan di deliver, timeline to be confirm
22 | clock in setelah submit, saat mau clock out, informasinya tidak tampil |  | noted akan di deliver, timeline to be confirm
23 | outbox tidak perlu ada untuk di mobile |  | noted
24 | Widget dashboard di take out |  | noted

## API 28-12-2020
Welcome | Employee Spotlight | My Profile | My Report / Getmyreport | Keterangan:
Employee Name | BIRTHDAY | Employee Name | LEAVE |  | Manual Input
Employee email | 1. Picture | Level | 1. Start Date |  | Tambahan API Urgent
External ID(APxxxxx) | 2. Employee Name |  | 2. End Date |  | Done
Email | 3. Division / Unit | PERSONAL DETAILS | 3. Leave Type |  | need to be revised
Image | 4. Birthday Date | * About Me | 4. Duration
Request & Approval | 5. Email | 1. Nick Name | 5. Reason
REQUEST / ESSnotification |  | 2. Employee ID (AP) | 6. status (approved / reject / revise)
1. Title Request | NEWCOMER | 3. Place, Date of Birth
2. Author | 1. Picture | 4. Religion | Attendance
3. Approval Date | 2. Employee Name | 5. Marital Status | 1. Start Date
4. Approver Name (Staging) | 3. Division / Unit | 6. Number of Childern | 2. End Date
5. Status | 4. Join Date | 7. Contact | 3. Start Time
6. Link to Form | 5. Email | 8. Address | 4. End Time
7. Author Email |  |  | 5. Attendace Type
8. Status: Finished/Unfinished | WEDDING | * Employee Details | 6. Notes
| 1. Picture | 1. employee location (jakarta/surabaya)
GIVE APPROVAL / Statusapv | 2. Employee Name | 2. Group (ECS, ICS, Senior Advisory, BOP)
1. Title Request | 3. Division / Unit | 3. LOB | My Dahboard
2. Author | 4. Wedding Date | 4. Email | My Leave
3. Approval Date |  | 5. Level | Remaining Annual Leave Quota
4. Approver Name (Staging) | NEW BORN | 6. Join Date | Remaining Kuota Cuti Besar
5. Status | 1. Picture Baby | 7. Division / Unit
6. Link to Form | 2. Employee Name | 8. Ext Number
7. Author Email | 3. Baby Name | 9. Phone
8. Status: Finished/Unfinished | 4. Born Date
My AAJ Inbox / Myaaj |  | * Educational Background
Title Request |  | 1. Degree
Approved By |  | 2. Major
Date & Time Notification |  | 3. University
Email |  | 4. Graduation Year
Link Status
Status Approval (finished/Unfinish) |  | * Professional Certification
1. Certification Name
Employee Directory |  | 2. Certification Number
Picture |  | 3. Released by
Name |  | 4. Released Start/from
employee location (jakarta/surabaya) |  | 5. Expired Date
Group (ECS, ICS, Senior Advisory, BOP)
lob/ non lob |  | * Licence
division / unit |  | 1. License Name
level |  | 2. License Number
ext number |  | 3. Released by
mobile number |  | 4. Released Start/from
email |  | 5. Expired Date
* Working Experiences:
a. Company
b. Location
c. Job Position
d. Job Description
e. Start Period
f. End Period
Level & Function
* Level
1. Level
2. LOB
3. Division / Unit
4. From
5. To
* Function / secondary job
1. Role
2. From
3. To

## REDMINE
TASK FOR ALIP |  | Notes Color | TASK FOR ADE
Welcome |  | Penambahan | Employee Directory
Employee Name |  | Revisi | Picture
External ID(APxxxxx) |  |  | Name
Email |  |  | employee location (jakarta/surabaya) | Get From PHRPA0002 field WorkLocation ( Fixed Value(01=Jakarta/ 02=Surabaya) )
Image |  |  | Group (ECS, ICS, Senior Advisory, BOP) | Get From PHRPA0002 Field GrupOrg join CHRPA02GROUP for get Description
lob/ non lob
Request & Approval |  |  | division / unit
REQUEST / ESSnotification |  |  | level
1. Title Request |  |  | ext number
2. Author |  |  | mobile number
3. Approval Date |  |  | email
4. Approver Name (Staging)
5. Status |  |  | * Employee Details
6. Link to Form |  |  | 1. employee location (jakarta/surabaya) | Get From PHRPA0002 field WorkLocation ( Fixed Value(01=Jakarta/ 02=Surabaya) )
7. Author Email | Get From PHRPA0012 (commType 0004 join PHRPACOMMTYP for get Description) |  | 2. Group (ECS, ICS, Senior Advisory, BOP) | Get From PHRPA0002 Field GroupOrg join CHRPA02GROUP for get Description
8. Status: Finished/Unfinished | Get From PCMWFRUNTASK field WorkFlowStatus ( F=Finished; U=UnFinished )/ RegID |  | 3. LOB
GIVE APPROVAL / Statusapv |  |  | 4. Email
1. Title Request |  |  | 5. Level
2. Author |  |  | 6. Join Date
3. Approval Date |  |  | 7. Division / Unit
4. Approver Name (Staging) |  |  | 8. Ext Number
5. Status |  |  | 9. Phone
6. Link to Form
7. Author Email | Get From PHRPA0012 (commType 0004 join PHRPACOMMTYP for get Description)
8. Status: Finished/Unfinished | Get From PCMWFRUNTASK field WorkFlowStatus ( F=Finished; U=UnFinished )/ RegID |  | Level & Function
* Level
My AAJ Inbox / Myaaj |  |  | 1. Level
Title Request |  |  | 2. LOB
Approved By |  |  | 3. Division / Unit
Date & Time Notification |  |  | 4. From
Email |  |  | 5. To
Link Status
Status Approval (finished/Unfinish) | Get From PCMWFRUNTASK field WorkFlowStatus ( F=Finished; U=UnFinished )/ RegID |  | * Function / secondary job | to be check oleh Infimedia, tidak perlu ditambahkan dulu
|  |  | 1. Role | Get From PHRPA0055 field Position join PHROM0001 where ObjectClass 'P' to get Description from ObjectID
My Report / Getmyreport |  |  | 2. From | Get From PHRPA0055 field StartDate
LEAVE | Get form PHRPA0018 |  | 3. To | Get From PHRPA0055 field EndDate
1. Start Date | Get from PHRPA0018 field StartDate
2. End Date | Get from PHRPA0018 field EndDate
3. Leave Type | Get from PHRPA0018 field AbsenceType
4. Duration | Get from PHRPA0018 field TotalAbsenceTaken
5. Reason | Get from PHRPA0018 field Notes
7. Period | Get from PHRPA0017 field StartDate (Hanya Tahunnya Saja) sesuai periode cuti di PHRPA0018 diambil

## Sheet3
TableName | FieldName | SeqNum | DataRef | DataType | Length | Prec | Scale | TableRef | FixedValue | SearchFunction | SearchType | IsPrimaryKey | IsIdentity | AllowNull | SelectFunction | IsIndexKey | IsDescIndexKey | FormatRef | DefaultValue | IsRequired | IsHidden | ReadOnly | ColumnNo | Sequence | GridView | ValueField | DisplayValue | LookupGrid | LookupFilter | LookupFunction | IsCustomizationFilter | ParamCombo | TriggerCombo | CreateBy | CreateDate | ChangeBy | ChangeDate
PHRPA0002 | ChangeBy | 27 | CHANGEBY | 0 | 18 | 0 | 0 |  | NULL |  |  | 0 | 0 | 1 |  | 0 | 0 |  |  | 0 | 0 | 0 | 2 | 22 | 0 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160725155959 | minovais | 20160907153922
PHRPA0002 | ChangeDate | 28 | CHANGEDT | 0 | 14 | 0 | 0 |  | NULL |  |  | 0 | 0 | 1 |  | 0 | 0 | datetime |  | 0 | 0 | 0 | 2 | 23 | 0 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160725155959 | minovais | 20160907153922
PHRPA0002 | CompanyID | 6 | COMPID | 0 | 4 | 0 | 0 | PCMEPCOMPID | NULL |  | 0 | 0 | 0 | 1 |  | 0 | 0 |  | 2000 | 1 | 0 | 0 | 1 | 6 | 1 | 0 | 0 | 0 | 0 | NULL | 1 |  | EmployeeArea | minovais | 20160725155959 | minovais | 20160907153920
PHRPA0002 | CostCenter | 16 | CC | 0 | 100 | 0 | 0 | PHROM0001 | NULL | CG-CG-CC | 3 | 0 | 0 | 1 |  | 0 | 0 |  |  | 0 | 0 | 0 | 2 | 15 | 1 | 0 | 0 | 0 | 0 | NULL | 1 | CC |  | minovais | 20160725155959 | minovais | 20160907153921
PHRPA0002 | CostCenterCust | 23 | CCCUST | 0 | 100 | 0 | 0 |  | NULL |  |  | 0 | 0 | 1 |  | 0 | 0 |  |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160725155959 | minovais | 20160907153922
PHRPA0002 | CreateBy | 25 | CREATEBY | 0 | 18 | 0 | 0 |  | NULL |  |  | 0 | 0 | 1 |  | 0 | 0 |  |  | 0 | 0 | 0 | 2 | 20 | 0 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160725155959 | minovais | 20160907153922
PHRPA0002 | CreateDate | 26 | CREATEDT | 0 | 14 | 0 | 0 |  | NULL |  |  | 0 | 0 | 1 |  | 0 | 0 | datetime |  | 0 | 0 | 0 | 2 | 21 | 0 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160725155959 | minovais | 20160907153922
PHRPA0002 | EffectiveDate | 4 | EFECTIVDATE | 0 | 100 | 0 | 0 |  | NULL |  |  | 0 | 0 | 0 |  | 0 | 0 | date |  | 0 | 1 | 0 | 2 | 19 | 0 | 0 | 0 | 0 | 0 | NULL | NULL | NULL | NULL | jesika | 20170506160603 | jesika | 20170506160603
PHRPA0002 | EmployeeArea | 7 | EMPAREA | 0 | 4 | 0 | 0 | PCMEPEMPAREA | NULL |  | 0 | 0 | 0 | 1 |  | 0 | 0 |  |  | 1 | 0 | 0 | 1 | 7 | 1 | 0 | 0 | 0 | 0 | NULL | 1 |  | EmployeeOffice | minovais | 20160725155959 | minovais | 20160907153920
PHRPA0002 | EmployeeID | 3 | EMPID | 0 | 4 | 0 | 0 |  | NULL | group |  | 1 | 0 | 0 |  | 0 | 0 |  |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160725155959 | minovais | 20160907153920
PHRPA0002 | EmployeeOffice | 8 | EMPOFF | 0 | 4 | 0 | 0 | PCMEPEMPOFF | NULL |  | 0 | 0 | 0 | 1 |  | 0 | 0 |  |  | 1 | 0 | 0 | 1 | 8 | 1 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160725155959 | minovais | 20160907153920
PHRPA0002 | EmployeeRegional | 30 |  | 0 | 1000 | 0 | 0 |  | NULL |  |  | 0 | 0 | 1 |  | 0 | 0 |  |  | 0 | 1 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | wanto | 20160725155959 | minovais | 20160907153922
PHRPA0002 | EmployeeStatus | 9 | EMPSTAT | 0 | 4 | 0 | 0 | PCMEPEMPSTAT | NULL |  | 0 | 0 | 0 | 1 |  | 0 | 0 |  | 01 | 1 | 0 | 0 | 1 | 9 | 1 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160725155959 | minovais | 20160907153921
PHRPA0002 | EmployeeSubType | 11 | EMPSTYP | 0 | 4 | 0 | 0 | PCMEPEMPSTYP | NULL |  | 0 | 0 | 0 | 1 |  | 0 | 0 |  |  | 1 | 0 | 0 | 1 | 11 | 1 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160725155959 | minovais | 20160907153921
PHRPA0002 | EmployeeType | 10 | EMPTYP | 0 | 4 | 0 | 0 | PCMEPEMPTYP | NULL |  | 0 | 0 | 0 | 1 |  | 0 | 0 |  |  | 1 | 0 | 0 | 1 | 10 | 1 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160725155959 | minovais | 20160907153921
PHRPA0002 | EndDate | 2 | EDATE | 0 | 8 | 0 | 0 |  | NULL |  |  | 1 | 0 | 0 |  | 0 | 0 | date | 31/12/9999 | 1 | 0 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160725155959 | minovais | 20160907153919
PHRPA0002 | Job | 15 | JOB | 0 | 18 | 0 | 0 | PHROM0001 | NULL | JF-JF-J-P | 3 | 0 | 0 | 1 |  | 0 | 0 |  |  | 0 | 0 | 1 | 2 | 18 | 1 | 0 | 0 | 0 | 0 | NULL | 1 | ObjectClass[=]J |  | minovais | 20160725155959 | minovais | 20160907153921
PHRPA0002 | JobCust | 22 | JOBCUST | 0 | 8 | 0 | 0 |  | NULL |  |  | 0 | 0 | 1 |  | 0 | 0 |  |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160725155959 | minovais | 20160907153922
PHRPA0002 | MovementReason | 5 | MOVR | 0 | 4 | 0 | 0 | PCMEPMOVR | NULL |  | 0 | 0 | 0 | 1 |  | 0 | 0 |  |  | 1 | 0 | 0 | 1 | 5 | 1 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160725155959 | minovais | 20160907153920
PHRPA0002 | MovementType | 4 | MOVTYP | 0 | 4 | 0 | 0 | PCMEPMOVTYP | NULL |  | 0 | 0 | 0 | 1 |  | 0 | 0 |  |  | 1 | 0 | 0 | 1 | 4 | 1 | 0 | 0 | 0 | 0 | NULL | 1 |  | MovementReason | minovais | 20160725155959 | minovais | 20160907153920
PHRPA0002 | Notes | 24 | NOTES | 0 | 500 | 0 | 0 |  | NULL |  |  | 0 | 0 | 1 |  | 0 | 0 |  |  | 0 | 0 | 0 | 2 | 19 | 1 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160725155959 | minovais | 20160907153922
PHRPA0002 | Organization | 13 | ORG | 0 | 18 | 0 | 0 | PHROM0001 | NULL |  |  | 0 | 0 | 1 |  | 0 | 0 |  |  | 0 | 0 | 1 | 2 | 16 | 1 | 0 | 0 | 0 | 0 | NULL | 1 | ObjectClass[=]O |  | minovais | 20160725155959 | minovais | 20160907153921
PHRPA0002 | OrganizationCust | 20 | ORGCUST | 0 | 60 | 0 | 0 |  | NULL |  |  | 0 | 0 | 1 |  | 0 | 0 |  |  | 0 | 0 | 0 | 2 | 17 | 0 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160725155959 | minovais | 20160907153922
PHRPA0002 | PayrollGroup | 12 | PGRUP | 0 | 4 | 0 | 0 | PHRPYPGRUP | NULL |  | 0 | 0 | 0 | 1 | var valueF = val.getValue(); var data_ = undefined; Ext.Ajax.request({ async : false, method : 'POST', url : '/UserControl/GetStore', params : { tableName : 'PHRPYPGCTRL', param : 'PayrollGroup[=]' + valueF }, success : function (response) { var results = Ext.decode(response.responseText); data_ = results.data; if (data_.length > 0) { var r = data_[0].PayrollControlStatus; if (r == 'V' ¦¦ r == 'S') { MinovaMessage(' n', 'PYVAL1', '', 'E'); } } } }); | 0 | 0 |  |  | 1 | 0 | 0 | 1 | 12 | 1 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160725155959 | minovais | 20160907153921
PHRPA0002 | Position | 14 | POS | 0 | 18 | 0 | 0 | PHROM0001 | NULL | O-O-P-E | 3 | 0 | 0 | 1 | var Mainform = Ext.ComponentQuery.query('[name=' + val.formname + ']')[0]; var _StartDate = Mainform.getForm().findField('StartDate').getValue(); var objClassValue = val.objClassValue; var hasil = undefined; var cc = null; Ext.Ajax.request({ | async : false, | method : 'POST', | url : '/UserControl/GetStore', | params : { |  | tableName : 'PHROM0006', |  | param : 'StartDate[<=]' + _StartDate + ',EndDate[>=]' + _StartDate + ',ObjectID[=]' + val.getValue() + ',ObjectClass[=]' + objClassValue | }, | success : function (response) { |  | var results = Ext.decode(response.responseText); |  | if (results.data.length > 0) { |  |  | hasil = results.data[0]; |  |  | Mainform.getForm().findField('Job').setValue(hasil.Job); |  |  | Mainform.getForm().findField('CostCenter').setValue(hasil.CostCenter); | } else { | Mainform.getForm().findField('Job').setValue(''); | Mainform.getForm().findField('CostCenter').setValue(''); | } | } }); var Org_ = null; Ext.Ajax.request({ | async : false, | method : 'POST', | url : '/UserControl/GetStore', | params : { | tableName : 'PHROM0002', | param : 'StartDate[<=]' + _StartDate + ',EndDate[>=]' + _StartDate + ',ObjectID[=]' + val.getValue() + ',ObjectClass[=]P,RelationshipDirectory[=]B,RelationshipClass[=]O' | }, | success : function (response) { | results = (response.responseText); | Org_ = Ext.decode(results); | if (Org_.data.length > 0) { | Org = Org_.data[0]; | Mainform.getForm().findField('Organization').setValue(Org.RelationshipObject); | console.log(Org.RelationshipObject) | } else { | Mainform.getForm().findField('Organization').setValue(''); | } | } }); if (Mainform.getForm().findField('CostCenter').getValue() == '') { | Ext.Ajax.request({ | async : false, | method : 'POST', | url : '/ORM/GetCostCenter?ObjectID=' + val.getValue() + '&class=' + objClassValue + '&keyDate=' + _StartDate + '&isOneLevel=false', | success : function (response) { | results = (response.responseText); | cc_ = Ext.decode(results); | cc = cc_.results.data; | Mainform.getForm().findField('CostCenter').setValue(cc); | } | }); } if (val.getValue() == '') { | Mainform.getForm().findField('Organization').setValue(''); | Mainform.getForm().findField('CostCenter').setValue(''); } | 0 | 0 | 0 | 0 | 0 | 2 | 14 | 1 | 0 | 0 | 0 | 0 | NULL | 1 | P | minovais | 20160725155959 | minovais | 20160907153921
PHRPA0002 | PositionCust | 21 | POSCUST | 0 | 60 | 0 | 0 |  | NULL |  |  | 0 | 0 | 1 |  | 0 | 0 |  |  | 0 | 1 | 0 | 2 | 15 | 0 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160725155959 | minovais | 20160907153922
PHRPA0002 | StartDate | 1 | SDATE | 0 | 8 | 0 | 0 |  | NULL |  |  | 1 | 0 | 0 |  | 0 | 0 | date |  | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160725155959 | minovais | 20160907153919
PHRPA0002 | SuratKerja | 19 | SK | 0 | 30 | 0 | 0 |  | NULL |  |  | 0 | 0 | 1 |  | 0 | 0 |  |  | 0 | 0 | 0 | 2 | 18 | 0 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160725155959 | minovais | 20160907153921
PHRPA0002 | SuratPerintahKerja | 18 | SPK | 0 | 30 | 0 | 0 |  | NULL |  |  | 0 | 0 | 1 |  | 0 | 0 |  |  | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160725155959 | minovais | 20160907153921
PHRPA0002 | TaxOffice | 17 | TAXOFF | 0 | 4 | 0 | 0 | PHRPYTAXOFF | NULL |  | 0 | 0 | 0 | 1 |  | 0 | 0 |  |  | 1 | 1 | 0 | 1 | 13 | 0 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160725155959 | minovais | 20160907153922
PHRPA0002 | WorkLocation | 25 | WLOCAT | 0 | 50 | 0 | 0 | CCMEPEMPWORKLOC | NULL |  | 0 | 0 | 0 | 1 |  | 0 | 0 |  |  | 0 | 1 | 0 | 1 | 23 | 0 | 1 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160725155959 | minovais | 20160907153922
CHRPA02GROUP | ChangeBy | 14 | CHANGEBY | 0 | 18 | 0 | 0 |  |  |  |  | 0 | 0 | 1 |  | 0 | 0 |  |  | 0 | 0 | 0 | 2 | 15 | 0 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160824142709 | minovais | 20170119170808
CHRPA02GROUP | ChangeDate | 15 | CHANGEDT | 0 | 14 | 0 | 0 |  |  |  |  | 0 | 0 | 1 |  | 0 | 0 | datetime |  | 0 | 0 | 0 | 2 | 16 | 0 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160824142709 | minovais | 20170119170808
CHRPA02GROUP | CreateBy | 12 | CREATEBY | 0 | 18 | 0 | 0 |  |  |  |  | 0 | 0 | 1 |  | 0 | 0 |  |  | 0 | 0 | 0 | 2 | 13 | 0 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160824142709 | minovais | 20170119170808
CHRPA02GROUP | CreateDate | 13 | CREATEDT | 0 | 14 | 0 | 0 |  |  |  |  | 0 | 0 | 1 |  | 0 | 0 | datetime |  | 0 | 0 | 0 | 2 | 14 | 0 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160824142709 | minovais | 20170119170808
CHRPA02GROUP | EndDate | 2 | EDATE | 0 | 8 | 0 | 0 |  |  |  |  | 1 | 0 | 0 |  | 0 | 0 | date |  | 1 | 0 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160824142709 | minovais | 20170119170807
CHRPA02GROUP | Notes | 11 | NOTES | 0 | 500 | 0 | 0 |  |  |  |  | 0 | 0 | 1 |  | 0 | 0 |  |  | 0 | 0 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160824142709 | minovais | 20170119170808
CHRPA02GROUP | StartDate | 1 | SDATE | 0 | 8 | 0 | 0 |  |  |  |  | 1 | 0 | 0 |  | 0 | 0 | date |  | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160824142709 | minovais | 20170119170807
CHRPA02GROUP | GroupType | 3 | Group | 0 | 4 | 0 | 0 |  |  |  |  | 1 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 1 | 4 | 1 | 1 | 0 | 0 | 0 | NULL | 1 |  |  | minovais | 20160824142709 | minovais | 20170119170807
CHRPA02GROUP | GroupTypeDesc | 4 | Group | 0 | 50 | 0 | 0 |  |  |  |  | 0 | 0 | 1 |  | 0 | 0 |  |  | 0 | 0 | 0 | 1 | 5 | 1 | 0 | 1 | 0 | 0 | NULL | 1 |  |  | minovais | 20160824142709 | minovais | 20170119170808
NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
19900101 | 99991231 | 0001 | ECS |  | captain | 20160101010101 | captain | 20160101010101
19900101 | 99991231 | 0002 | ICS |  | captain | 20160101010101 | captain | 20160101010101
19900101 | 99991231 | 0003 | Senior Advisory |  | captain | 20160101010101 | captain | 20160101010101
19900101 | 99991231 | 0004 | BOP |  | captain | 20160101010101 | captain | 20160101010101